# Problem 4 Solution: Concert Stage Setup Worker Assignment

## Problem Setup

Given:

Workers and Availability:

| Worker | Hours Available | Hourly Rate |

|--------|----------------|-------------|

| 1 | 20 | $20 |

| 2 | 18 | $18 |

| 3 | 15 | $15 |

| 4 | 10 | $12 |

Tasks and Requirements:

| Task | Description | Hours Required |

|------|-------------|----------------|

| 1 | Structure building | 20 |

| 2 | Electrical wiring | 15 |

Total work needed: 35 hours

Total availability: 63 hours

Objective: Minimize total labor cost while completing all tasks

## Part (a): Integer Linear Optimization Formulation

### Decision Variables

Integer variables:

**x_{i,j}** = number of hours worker i spends on task j

i ∈ {1, 2, 3, 4} (workers)

j ∈ {1, 2} (tasks: 1=structure, 2=electrical)

x_{i,j} ∈ Z+ (non-negative integers)

This gives us 8 decision variables: x_{1,1}, x_{1,2}, x_{2,1}, x_{2,2}, x_{3,1}, x_{3,2}, x_{4,1}, x_{4,2}

### Objective Function

Minimize total cost:

Cost = (hourly rate of worker) × (hours worked by worker on all tasks)

Minimize:

20·(x_{1,1} + x_{1,2})    // Worker 1 total hours × $20/hr

+ 18·(x_{2,1} + x_{2,2})  // Worker 2 total hours × $18/hr

+ 15·(x_{3,1} + x_{3,2})  // Worker 3 total hours × $15/hr

+ 12·(x_{4,1} + x_{4,2})  // Worker 4 total hours × $12/hr

Or expanded:

Minimize: 20x_{1,1} + 20x_{1,2} + 18x_{2,1} + 18x_{2,2} + 15x_{3,1} + 15x_{3,2} + 12x_{4,1} + 12x_{4,2}

### Constraints

1. Task Completion Constraints (ensure all work is done):

// Task 1 (Structure building): 20 hours required

x_{1,1} + x_{2,1} + x_{3,1} + x_{4,1} = 20

// Task 2 (Electrical wiring): 15 hours required

x_{1,2} + x_{2,2} + x_{3,2} + x_{4,2} = 15

2. Worker Availability Constraints (don't exceed available hours):

// Worker 1: max 20 hours

x_{1,1} + x_{1,2} ≤ 20

// Worker 2: max 18 hours

x_{2,1} + x_{2,2} ≤ 18

// Worker 3: max 15 hours

x_{3,1} + x_{3,2} ≤ 15

// Worker 4: max 10 hours

x_{4,1} + x_{4,2} ≤ 10

3. Non-negativity and Integer Constraints:

x_{i,j} ≥ 0    for all i ∈ {1,2,3,4}, j ∈ {1,2}

x_{i,j} ∈ Z    (integers)

### Complete Formulation Summary

Decision Variables: x_{i,j} ∈ Z+ for i=1..4, j=1..2 (8 integer variables)

Objective Function:

Minimize: Σ_{i=1 to 4} Σ_{j=1 to 2} (rate_i × x_{i,j})

= 20(x_{1,1}+x_{1,2}) + 18(x_{2,1}+x_{2,2}) + 15(x_{3,1}+x_{3,2}) + 12(x_{4,1}+x_{4,2})

Subject to:

// Task completion (equality)

x_{1,1} + x_{2,1} + x_{3,1} + x_{4,1} = 20

x_{1,2} + x_{2,2} + x_{3,2} + x_{4,2} = 15

// Worker availability (inequality)

x_{1,1} + x_{1,2} ≤ 20

x_{2,1} + x_{2,2} ≤ 18

x_{3,1} + x_{3,2} ≤ 15

x_{4,1} + x_{4,2} ≤ 10

// Non-negativity and integer

x_{i,j} ≥ 0, x_{i,j} ∈ Z for all i,j

## Part (b): Excel Implementation and Solution

### Excel Setup

1. Decision Variables Table:

|   | Structure (Task 1) | Electrical (Task 2) |

|---|-------------------|---------------------|

| Worker 1 ($20/hr) | x_{1,1} | x_{1,2} |

| Worker 2 ($18/hr) | x_{2,1} | x_{2,2} |

| Worker 3 ($15/hr) | x_{3,1} | x_{3,2} |

| Worker 4 ($12/hr) | x_{4,1} | x_{4,2} |

| Total Hours | =SUM (should be 20) | =SUM (should be 15) |

2. Worker Hours and Costs:

| Worker | Hours Used | Capacity | Cost |

|--------|------------|----------|------|

| 1 | =x_{1,1}+x_{1,2} | 20 | =20×hours_used |

| 2 | =x_{2,1}+x_{2,2} | 18 | =18×hours_used |

| 3 | =x_{3,1}+x_{3,2} | 15 | =15×hours_used |

| 4 | =x_{4,1}+x_{4,2} | 10 | =12×hours_used |

| Total | | | =SUM(costs) |

3. Solver Settings:

**Objective:** Minimize total cost cell

**Variables:** All 8 x_{i,j} cells

**Constraints:**

Task 1 total = 20

Task 2 total = 15

Worker 1 hours ≤ 20

Worker 2 hours ≤ 18

Worker 3 hours ≤ 15

Worker 4 hours ≤ 10

All x_{i,j} ≥ 0

All x_{i,j} = integer

**Solving Method:** Simplex LP with integer constraints

### Optimal Solution Analysis

Intuition: Since all workers are equally capable on both tasks, the optimal solution will assign cheaper workers first.

Expected Optimal Solution:

| Worker | Structure Hours | Electrical Hours | Total Hours | Cost |

|--------|----------------|------------------|-------------|------|

| 1 ($20) | 0 | 0 | 0 | $0 |

| 2 ($18) | 0 | 0 | 0 | $0 |

| 3 ($15) | 15 | 0 | 15 | $225 |

| 4 ($12) | 5 | 10 | 10 | $120 |

| OR alternative | | | | |

| 4 ($12) | 10 | 0 | 10 | $120 |

| 3 ($15) | 10 | 15 | 25 | $375 |

| TOTAL | 20 | 15 | 35 | $495 |

Wait, let me recalculate:

Strategy: Use cheapest workers first

Worker 4 ($12/hr): Use all 10 hours

Worker 3 ($15/hr): Use all 15 hours

Worker 2 ($18/hr): Use 10 hours (since we need 35 total)

Worker 1 ($20/hr): Use 0 hours

Total: 10 + 15 + 10 = 35 hours

Cost: 10×$12 + 15×$15 + 10×$18 = $120 + $225 + $180 = $525

Optimal Assignment:

| Worker | Rate | Structure | Electrical | Total | Cost |

|--------|------|-----------|------------|-------|------|

| 4 | $12 | 10 | 0 | 10 | $120 |

| 3 | $15 | 10 | 5 | 15 | $225 |

| 2 | $18 | 0 | 10 | 10 | $180 |

| 1 | $20 | 0 | 0 | 0 | $0 |

| Total | | 20 | 15 | 35 | $525 |

Optimal Objective Value: $525

(Note: There may be multiple optimal solutions with the same cost depending on task assignment, but total cost remains $525)

## Part (c): Additional Safety and Union Rule Requirements

### Requirement R1: At least 3 workers must work on structure building

New Binary Variable:

**z_i ∈ {0,1}** for i ∈ {1,2,3,4}

z_i = 1 if worker i works ANY hours on structure building (task 1)

z_i = 0 otherwise

New Constraints:

Link binary to hours worked:

x_{1,1} ≤ 20·z_1    // If z_1 = 0, then x_{1,1} must be 0

x_{2,1} ≤ 18·z_2    // If z_2 = 0, then x_{2,1} must be 0

x_{3,1} ≤ 15·z_3    // If z_3 = 0, then x_{3,1} must be 0

x_{4,1} ≤ 10·z_4    // If z_4 = 0, then x_{4,1} must be 0

Minimum 3 workers on structure:

z_1 + z_2 + z_3 + z_4 ≥ 3    (R1)

Alternative formulation using "big M":

The "M" values above (20, 18, 15, 10) are the maximum hours each worker could work on task 1, which serves as the "big M" for each worker.

### Requirement R2: Worker 3 can work on structure OR electrical, but NOT both

New Binary Variable:

**y_3 ∈ {0,1}**

y_3 = 1 if worker 3 works on structure building (task 1)

y_3 = 0 if worker 3 works on electrical wiring (task 2)

New Constraints:

// If y_3 = 1 (structure), then electrical hours must be 0

x_{3,2} ≤ 15·(1 - y_3)

// If y_3 = 0 (electrical), then structure hours must be 0

x_{3,1} ≤ 15·y_3

Alternative formulation (simpler):

// Worker 3 can only work on one task

// If working on structure, cannot work on electrical and vice versa

x_{3,1} ≤ 15·w_{3,1}        // w_{3,1} = 1 allows structure work

x_{3,2} ≤ 15·w_{3,2}        // w_{3,2} = 1 allows electrical work

w_{3,1} + w_{3,2} ≤ 1       // Can only choose one task (R2)

where w_{3,1}, w_{3,2} ∈ {0,1}

Even simpler (direct constraint):

Since Worker 3 can work on one task OR the other but not both:

// If x_{3,1} > 0, then x_{3,2} = 0 and vice versa

// This can be enforced by:

x_{3,1} ≤ 15·b_3            // b_3 = 1 allows structure

x_{3,2} ≤ 15·(1 - b_3)      // b_3 = 0 allows electrical

where b_3 ∈ {0,1}    (R2)

### Requirement R3: If Worker 4 works on electrical, must work ≥5 hours on electrical

New Binary Variable:

**u_4 ∈ {0,1}**

u_4 = 1 if worker 4 works on electrical wiring (task 2)

u_4 = 0 otherwise

New Constraints:

// If worker 4 works any hours on electrical, u_4 must be 1

x_{4,2} ≤ 10·u_4            // Upper bound: if u_4 = 0, then x_{4,2} = 0

// If u_4 = 1, then must work at least 5 hours

x_{4,2} ≥ 5·u_4             // Lower bound: if u_4 = 1, then x_{4,2} ≥ 5

where u_4 ∈ {0,1}    (R3)

Explanation:

First constraint: If u_4 = 0, forces x_{4,2} ≤ 0, so x_{4,2} = 0

Second constraint: If u_4 = 1, forces x_{4,2} ≥ 5

Together: Either x_{4,2} = 0 (not working on electrical) OR x_{4,2} ≥ 5 (working at least 5 hours)

The constraints prevent the "middle ground" of 1-4 hours

### Complete Extended Formulation

Additional Binary Variables:

z_i ∈ {0,1}    for i = 1,2,3,4    (R1: worker i works on structure)

b_3 ∈ {0,1}                        (R2: worker 3's task choice)

u_4 ∈ {0,1}                        (R3: worker 4 works on electrical)

Additional Constraints:

For R1 (at least 3 workers on structure):

x_{1,1} ≤ 20·z_1

x_{2,1} ≤ 18·z_2

x_{3,1} ≤ 15·z_3

x_{4,1} ≤ 10·z_4

z_1 + z_2 + z_3 + z_4 ≥ 3

For R2 (worker 3 on one task only):

x_{3,1} ≤ 15·b_3

x_{3,2} ≤ 15·(1 - b_3)

For R3 (worker 4 electrical minimum):

x_{4,2} ≤ 10·u_4

x_{4,2} ≥ 5·u_4

## Part (d): Excel Implementation with Extended Requirements

### Modified Excel Setup

Additional columns for binary variables:

z_1, z_2, z_3, z_4 (works on structure indicator)

b_3 (worker 3 task choice)

u_4 (worker 4 on electrical indicator)

Modified Solver Settings:

Same objective: Minimize total cost

Variables: 8 x_{i,j} + 6 binary variables

Constraints: All from part (a) PLUS:

x_{1,1} ≤ 20·z_1

x_{2,1} ≤ 18·z_2

x_{3,1} ≤ 15·z_3

x_{4,1} ≤ 10·z_4

z_1 + z_2 + z_3 + z_4 ≥ 3 (R1)

x_{3,1} ≤ 15·b_3 (R2)

x_{3,2} ≤ 15·(1-b_3) (R2)

x_{4,2} ≤ 10·u_4 (R3)

x_{4,2} ≥ 5·u_4 (R3)

All binary variables ∈ {0,1}

### Expected Optimal Solution with Extended Requirements

Analysis of constraints:

**R1 effect:** Must use at least 3 workers on structure (20 hours total)

This may force using more expensive workers

**R2 effect:** Worker 3 ($15/hr) can only work on ONE task

Reduces flexibility but worker 3 is relatively cheap

**R3 effect:** Worker 4 ($12/hr) either doesn't do electrical OR does ≥5 hours

Worker 4 is cheapest, so we want to use them

Optimal strategy considering all constraints:

Scenario 1: Worker 4 doesn't do electrical (u_4 = 0)

Need 15 hours electrical from workers 1, 2, 3

Need 20 hours structure from at least 3 workers

Worker 3 can do one or the other

Scenario 2: Worker 4 does ≥5 hours electrical (u_4 = 1, x_{4,2} ≥ 5)

Worker 4: 5+ hours electrical, rest on structure

Still need 2+ other workers on structure (R1)

Likely Optimal Solution:

| Worker | Rate | Structure | Electrical | z_i | Cost |

|--------|------|-----------|------------|-----|------|

| 4 | $12 | 5 | 5 | 1 | $120 |

| 3 | $15 | 0 | 10 | 0 | $150 |

| 2 | $18 | 10 | 0 | 1 | $180 |

| 1 | $20 | 5 | 0 | 1 | $100 |

| Total | | 20 | 15 | 3 | $550 |

Check constraints:

R1: z_1 + z_2 + z_4 = 3 ✓ (at least 3 workers on structure)

R2: Worker 3 only on electrical ✓ (x_{3,1} = 0, x_{3,2} = 10)

R3: Worker 4 on electrical with 5 hours ✓ (x_{4,2} = 5 ≥ 5)

Optimal Objective Value (Part c): $550

Comparison:

Part (b) optimal: $525

Part (d) optimal: $550

Cost increase: $25 (4.8% increase due to additional constraints)

## Summary

### Problem 4 Key Insights

**Worker-Task Assignment:** Classic bipartite matching problem

**Cost Minimization:** Prefer cheaper workers when all are equally skilled

**Constraint Impact:** Additional operational rules increase cost

**Binary Variable Tricks:**

Minimum participation (R1): Use indicators + count

Mutual exclusivity (R2): Use choice binary

Conditional minimum (R3): Use IF-THEN structure

### Formulation Progression

| Version | Variables | Constraints | Optimal Cost |

|---------|-----------|-------------|--------------|

| Part (a-b) | 8 integer | 6 | $525 |

| Part (c-d) | 8 integer + 6 binary | 15 | $550 |

### Key Techniques Used

R1 (At least k must participate):

Pattern: Create indicators z_i, link to x_i, count: Σz_i ≥ k

R2 (Mutually exclusive tasks):

Pattern: Create binary b, enforce: x_1 ≤ M·b, x_2 ≤ M·(1-b)

R3 (Conditional minimum):

Pattern: Create indicator u, enforce: x ≤ M·u AND x ≥ minimum·u

Result: Either x = 0 OR x ≥ minimum

These patterns are widely applicable in workforce scheduling, project management, and resource allocation problems.

Solution prepared for 15.060 Deliverable 8, Fall 2025